## Sheet1
Date | 2016-10-10 | Broderick Hyman | Aaron Brainard | Adam Hubbell
Task | Asignee | Time Est. | Risk | Actual Time | % Complete | Review
Directory Structure | Brodie | 1 hr. | 1 |  | 75
Make a makefile | Brodie | 1 hr. | 2
Research IEEE floating point | Aaron | 2 hrs. | 5
Coding standards | Adam | 2 hrs. | 5
Quad solver alpha test | Adam | 4 hrs. | 3