## Sheet1
Date | 2016-10-24 | Broderick Hyman | Aaron Brainard | Adam Hubbell
Task | Asignee | Time Est. | Risk | Actual Time | % Complete | Review
Mock up solar algo tests | Brodie | 2 hrs | 40% | 2.5 hrs | 100% | Adam
Read 1st chapter of solar book | Adam | 2 hrs | 10%
Read 1st chapter of solar book | Aaron | 2 hrs | 10%
Read 1st chapter of solar book | Brodie | 2 hrs | 10% | 3 hrs | 100%