## Sheet1
Date | 2016-12-14 | Broderick Hyman | Aaron Brainard | Adam Hubbell
Task | Asignee | Time Est. | Risk | Actual Time | % Complete | Review
Come up with user stories for Sunseeker | All | 2 hrs | 50% |  | 0%
Platform writeup | Brodie | 1 hour | 10% | 45 min | 100% | Aaron
Ownership and NDA | Adam | 1 hour | 30% | 30 min | 100% | Brodie
Gantt Chart | Aaron | 1 hr | 10% | 30 min | 100% | Adam