## Main
Solar Car Performance Modeling |  |  | Aaron Brainard
CS 4910: Senior Design |  |  | Adam Hubbell
2017-04-23 |  |  | Broderick Hyman
Speed and power management are crucial during a multi-day solar car race. A combined simulation of environmental and vehicular models allow the solar car team to optimize these parameters. A Java-based performance modeling application was created to determine optimal driving speed during the race. The application has the ability to adapt to solar car configurations, in order to assist the design process. This provides several tools that can help the team develop a winning race strategy, both before and during the race.
Chief Strategist
The user is a member of the Sunseeker team. This user does not have an in-depth knowledge of the car workings.
User will read the optimal speed for current road segment and relay information to driver
Cartographer
This person will use the route editing tool to recreate the route from the information given by the competition
Lead Engineer
This person knows how the car works, and will set up the config file
Model
Contains Aero, Rolling, Battery, Solar, Gravity, Motor calculations
Data
Google elevation and route data
Openweathermap weather data
Car configuration from Sunseeker team
Stories | Time Est. | Risk | % Complete
General
Configure application to be used with several car configs | 2 | 3 | 100
Chief Strategist edits route during race | 6 | 5 | 20
Cartographer creates route before race | 10 | 6 | 100
UI
Display Map with optimal speed overlay | 5 | 6 | 20
Display current and future weather | 3 | 2 | 80
Display graph of estimated battery vs actual | 3 | 2 | 50
Display current wind direction and velocity | 6 | 4 | 25
Graph of elevation | 3 | 2 | 100
Real-time charts of car data | 6 | 6 | 30
Weather
Chief Strategist can edit current weather if different | 2 | 2 | 100
Wind, sun and cloud weather data | 4 | 4 | 100
Road
Chief Strategist update shade percentage for road segment | 4 | 5 | 100
Update location from GPS | 4 | 3 | 75
Models
Calculate optimal speed estimates for all points of the race | 8 | 9 | 100
Adjust optimal speed estimates based on telemetry data | 4 | 6 | 30
System
Windows
Platform
JavaFX Application
NDA
None Needed
Ownership
Owned and maintained by Sunseeker RSO

## Notes
Short explanation of project
Describe user
Use display rather than read
Model should contain all pieces
Describe model components
Display percentage of solar power
Tool for speed limits
Overlay on google map
describe tool and how user will use it
-Define actors... map guy, weather data guy, etc. Puts in pieces beforehand
-Driver, who uses it during the race
-